## Checklist Library
Stage Name | Inspection Checklist Item
1. Earth work Excavation
1. Earth work Excavation | 1 Check for Setting out and Levels/Set backs as per Excavation Scheme plan.
1. Earth work Excavation | 2 Check for Layout of Excavation with reference to grids and keeping allowance from face of substructure.
1. Earth work Excavation | 3 Ensure protection of existing services /Neighbors Plot boundary
1. Earth work Excavation | 4 Ensure proper access for Trucks / Dumpers and other vehicles.
1. Earth work Excavation | 5 Depth of the Excavation
1. Earth work Excavation | 6 PCC Bottom level
1. Earth work Excavation | 7 Verify the foundation data with respect to geotechnical report.
1. Earth work Excavation | 8 Check for soil dressing, loose earth removed and area is leveled.
1. Earth work Excavation | 9 Check for the soil preserved at site for backfilling and dispose soil not suitable for filling.
1. Earth work Excavation | 10 All area well illuminated and ensure proper barricading the excavated area.
10. Slabs and beams shuttering | 1 Height of the slab level
10. Slabs and beams shuttering | 2 Quality of shuttering material
10. Slabs and beams shuttering | 3 Width and Depth of the beams as per the drawings
10. Slabs and beams shuttering | 4 Line alignments ,Level and Plumb of the beams
10. Slabs and beams shuttering | 5 Individual level and thickness of each bay of slab.
10. Slabs and beams shuttering | 6 Location & depth of sunken slab
10. Slabs and beams shuttering | 7 Water tightness near junctions of columns & beams.
10. Slabs and beams shuttering | 8 Cut out provisions for the duct/skylight
10. Slabs and beams shuttering | 9 Support to vertical joint of shuttering for 0.6 m beam or 0.8 m for slab
11. Slabs and beams steel fabrication
11. Slabs and beams steel fabrication | Reinforcement 1 Reinforcement bars are free from rust,mill scales, cleaned concrete droppings and any other such impurities
11. Slabs and beams steel fabrication | 2 Diameter of bars
11. Slabs and beams steel fabrication | 3 Bottom bars, top bars, bent-up bars, stirrups, a distance of bent-up (crank) bars from the face of supports, spacing of the stirrups as per structural drawing, proper tying of stirrups f the beams
11. Slabs and beams steel fabrication | 4 Side covers and bottom covers for beams are provided
11. Slabs and beams steel fabrication | 5 Development length (L-bent) for the beams
11. Slabs and beams steel fabrication | 6 Spacing of bars as per the structural drawing
11. Slabs and beams steel fabrication | 7 Chair below each & every bent-up bars
11. Slabs and beams steel fabrication | 8 Distance of bent ups from the face of the beam
11. Slabs and beams steel fabrication | 9 Stirrups in a column for upper floor column size
11. Slabs and beams steel fabrication | MEP works 10 a.Electrical- All junctions & and all electrical layout, position of fan points, DB sleeves, junction boxes.
11. Slabs and beams steel fabrication | 11 b.Plumbing (WCs,Water supply & Drain Sleeves provisions)
11. Slabs and beams steel fabrication | 12 c.HVAC sleeves and duct provisions
11. Slabs and beams steel fabrication | 13 d.Smart system sleeves provisions
11. Slabs and beams steel fabrication | 14 e.Fire (if any requirement)
12.Grade slab | 1 To check the Backfilling has done until the required level
12.Grade slab | 2 FDT result has submitted and reviewed?
12.Grade slab | 3 To check the thicknes of the grade slab as per the drawing
12.Grade slab | 4 1000 gauge polythene sheet provided
12.Grade slab | 5 Antitermite treatment has done
12.Grade slab | 6 Intermediate -level marks are provided
12.Grade slab | 7 BRC mesh provided
12.Grade slab | 8 The thickness of the BRC mesh provided as per the drawing requirment
12.Grade slab | 9 The 20cm lapping provided between the BRC mesh
14.Column steel Fabrication | 1 The dimensions of column (length, breadth and depth).
14.Column steel Fabrication | 2 Reinforcement of the column as per the drawing
14.Column steel Fabrication | 3 The spacing between the stirrups are provided as per the drawing
14.Column steel Fabrication | 4 Check proper binding (Double strand)
14.Column steel Fabrication | 5 Laps provided as per the requirement
14.Column steel Fabrication | 6 Reinforcement bars are free from rust,mill scales, cleaned concrete droppings and any other such impurities
14.Column steel Fabrication | 7 Provisions of temporary supports is given to keep column steels in the vertical plumb and avoid the twisting of the steels .
14.Column steel Fabrication | 8 Provisions of cover blocks/thickness of the cover blocks
14.Column steel Fabrication | 9 The enough lap length has extended for the next stage?
15.Column Shuttering work | 1 Formwork including form oil applied and laid to the correct dimensions including line, level and plumb checked.
15.Column Shuttering work | 2 The verticality of the column shuttering using a plumb
15.Column Shuttering work | 3 The dimensions of column (length, breadth and depth).
15.Column Shuttering work | 4 Right angle at the corners of column shuttering
15.Column Shuttering work | 5 The proper support is given to the column or not
15.Column Shuttering work | 6 All the supports are rested over the stable/rigid place?
15.Column Shuttering work | 7 All gaps are properly sealed or not
15.Column Shuttering work | 8 The marking of concrete pouring level.(The bottom of the beam level)
15.Column Shuttering work | 9 Provisions of cover blocks at the top
15.Column Shuttering work | 10 Provisions of butterflies ,wherever the Blockwork comes in the column surface
15.Column Shuttering work | 11 Provisions of dowel bars ,wherever the doors/windows opening nearby the column
15.Column Shuttering work | 12 Any MEP provisions has provided or not
16. Block work | 1 Type of Block
16. Block work | 2 Cement, Fine aggregates (Sand)
16. Block work | 2 Measuring box for sand and measuring can for water available
16. Block work | 3 Thickness of joint
16. Block work | 4 Block work conforms to geometric tolerances as per specifications :
16. Block work | a. Plumb
16. Block work | b. Levels
16. Block work | c. Right angle
16. Block work | 7 Pointing done neatly(if applicable)
16. Block work | 8 Lintels as per the specifications and correctly installed
16. Block work | 9 Sizes of Rooms
16. Block work | 10 Sizes of opening checked and approved for
16. Block work | a. Doors
16. Block work | b. Windows
16. Block work | c. Cut outs
16. Block work | d. Any other opening
17.Consealed work before plastering & Plaster preparation | Consealed work 1 Wall chasing is done by grinder & chaser
17.Consealed work before plastering & Plaster preparation | 2 Wall chasing is done as per the required sizes
17.Consealed work before plastering & Plaster preparation | 3 All pipes diameters are as per required
17.Consealed work before plastering & Plaster preparation | 4 All pipes are laid in positions
17.Consealed work before plastering & Plaster preparation | 5 Pressure tested for plumbing pipes
17.Consealed work before plastering & Plaster preparation | 6 All Switches,Sockets,other points are provided as per the drawing/Client reqmt
17.Consealed work before plastering & Plaster preparation | 7 All MEP fixtures locations are as per drawing/clients reqmnt
17.Consealed work before plastering & Plaster preparation | 8 All chased area filled with richmortar/Concrete.
17.Consealed work before plastering & Plaster preparation | Plaster preparation 9 All the masonry joints are completely racked
17.Consealed work before plastering & Plaster preparation | 10 The Aluminium/Fibre mesh fixed or not over the column, beam, & wall masonry joining line, concealed wiring ducts, & over the concealed wall cuttings. .
17.Consealed work before plastering & Plaster preparation | 11 All the concealed electrical wire work , electrical conduits, junction box, concealed switch point, etc. should be noted for their proper position.
17.Consealed work before plastering & Plaster preparation | To ensure that all the concealed plumbing work is complete as per the drawing. The concealed pipeline should be checked for its water tightness & material quality, as per the specification.
17.Consealed work before plastering & Plaster preparation | 12 pullmark ( Button mark ) provided with proper aligning (Vertical plumb ,Right angle)
17.Consealed work before plastering & Plaster preparation | 13 Curing -Tocheck the curing of plastr prepared area (Minimum - 7 days)
18.Plastering | 1 To check for the Quality of materials (Cement ,sand,water.,)
18.Plastering | 2 To check the Level Mark (Pull Mark) should be made over the masonry surface at regular intervals. The thickness of the Pull Mark at the wall corners should be taken as 12mm.
18.Plastering | 3 To check the mortar mix ratio .1:3 or 1:4
18.Plastering | 4 To check the mortar mixed prepared by measuring box with proper water cement ratio
18.Plastering | 5 To check the CM mixing time -the mortar should nbe utized within hour after mixing
18.Plastering | 6 The right angle of the rooms
18.Plastering | 7 To check all the elevational features and window and door opening as per the architectural drawing
18.Plastering | 8 Is there an undulations in the wallsurface
18.Plastering | 9 Curing - To check the curing work of the plaster (Minimum 10 days)
19.Floor tiling | Prepration (Before tiling) 1 To check the Cleaning of the slab off loose mortar/material,etc.,
19.Floor tiling | 2 To check levels,Mortar thickness,button marking
19.Floor tiling | 3 To check availability of Materials - Sand ,tiles
19.Floor tiling | 4 Approved Layout of the tiles has followed
19.Floor tiling | 5 To ensure all MEP works below the tiles are done
19.Floor tiling | During Tiling 6 Line/level fixed,& slaopes are checked
19.Floor tiling | 7 To check difference in colour shade of tiles and replace with same batch/lot
19.Floor tiling | 8 Proportion of bedding mortar mixing
19.Floor tiling | 9 Proper spacers are used
19.Floor tiling | 10 Check the skirting for projection ,Rightangle
19.Floor tiling | After tiling 11 No material stacked afterr fixing?(Crack,scratches & damage)
19.Floor tiling | 12 To check the tiles surface cleaned properly
19.Floor tiling | 13 To check the hollow sounds
19.Floor tiling | 14 Are there cracked tiles? It should be replaced.
19.Floor tiling | 15 To check the pointing and grouting between the tiles joints
19.Floor tiling | 16 Curing-For minimum 4 days after grouting
2.PCC | 1 Check for location / Bottom level of footing
2.PCC | 2 The surface compaction completed
2.PCC | 3 FDT report submitted for review
2.PCC | 4 Check for formwork including form oil applied and laid to the correct dimensions including line,
2.PCC | 5 Check for concrete top level marked at required places
2.PCC | 6 1000-guage Polythene sheet providedetc.
20.Wall tiles | 1 Materials as approved sample
20.Wall tiles | 2 Tiles sizes are consistant (tolerance +/- 1%) for width and length
20.Wall tiles | 3 Tensure no difference in color tone,stain,crack and chipped off defected
20.Wall tiles | 4 The rough plaster has done with proper plumb and in right angles at the corners
20.Wall tiles | 5 Tiles are 2 hours soaked in water before using it
20.Wall tiles | 6 The spacers are used for the specific thickness of the joints between the tiles
20.Wall tiles | 7 vertical and horizontal alignment are in order ( deviation not more than 3mm)
20.Wall tiles | Laid correct pattern (If patern drawing supplied by client)
20.Wall tiles | 8 The tile is cut in proper shape and size at the plumbing outlets.
20.Wall tiles | 9 Tiles are neatly cut at corner,edge of wall,socket and switches
20.Wall tiles | 10 The corner beads are fixed as per the requirement
20.Wall tiles | 11 No mortar stains and paint drios
20.Wall tiles | 12 The bottom most line tiles is properly cutted and installed as per the floor tiling slope
20.Wall tiles | 13 Curing - To check the curing work of the tiles
20.Wall tiles | 14 To check any hollowness detected
20.Wall tiles | 15 The joints are properly filled with special adhesives /epoxy grout/cementitious grouts
21.plumbing work | 1 All plumbing and water supply lines are approved by clients
21.plumbing work | 2 All water supply and drainage pipes are laid as per drawing/Clients requirement
21.plumbing work | 3 All sanitary layout are approved by client
21.plumbing work | 4 All sanitary item/ layout are approved by client
21.plumbing work | 5 All sanitary installed as per the client requirement
21.plumbing work | 6 Floor gratings are installed
21.plumbing work | Instructions :-
22.Electrical work | Sl No Item Description Yes No N/A Remarks
22.Electrical work | 1 All wires and cables are laid as per the requirement
22.Electrical work | 2 All MCB,Isolators,ELCBs are istalled as per DB schedule/Requirement
22.Electrical work | 3 All electrical circuits are installed as per the DB schedule/Requirement
22.Electrical work | 4 Switch and Sockets are fixed as per the requirement
22.Electrical work | 5 Lights are installed as per the requirement
22.Electrical work | 6 AC indoor outdoor units are fixed as per the requirement
22.Electrical work | 7 Smart systems are fixed as per the requirement
23.Septic tank or Holding tank | 1 Location of the Septic tank /Holding tank
23.Septic tank or Holding tank | 2 Ensure the drawing for Septic tank or Holding tank
23.Septic tank or Holding tank | 3 Check the location is suitable for Septic tank
23.Septic tank or Holding tank | 4 To check the Compaction at the formation level (Test report)
23.Septic tank or Holding tank | 5 To check the Base of the Septic/Holding Tank done as per the drawing
23.Septic tank or Holding tank | 6 To check the RCC wall for the Holding tank as per the drawing/Sepecs
23.Septic tank or Holding tank | 7 To check the Solid block walls for the septic tank as per the drawings/specs
23.Septic tank or Holding tank | 8 To check the Soak pit done as per requirment
23.Septic tank or Holding tank | 9 To water proofing as per the drawing / location
23.Septic tank or Holding tank | 10 To check the slab sone as per drawing/specs
23.Septic tank or Holding tank | 11 To check the Bitumen application of the outer side
23.Septic tank or Holding tank | 12 To check inlet and outlet Pipes done proper as required
23.Septic tank or Holding tank | 13 To check Air vent provision
23.Septic tank or Holding tank | 14 To check Man hole provision as required
23.Septic tank or Holding tank | 15 Is there any seepage observed on the wall of floor below
24.Painting work | Prepration 1 To check for any wall cracks,Curing period completed or not
24.Painting work | 2 To check the materials/paints
24.Painting work | 3 To check color shade approved
24.Painting work | 4 To check the cleaning of the walls(Scrapping),Surface finishing
24.Painting work | 5 To ensure ,if any dampness,leakages and repaired
24.Painting work | 6 To check other materials are covered neatly with masking tape (Protection of other materials from damage like electrical switches,doors,windows ,glass partitions,etc.,
24.Painting work | Priming & Putty application 7 To check the application of priming coat has done with proper coverage(Manufacturer instructions)
24.Painting work | 8 To check the application of putty- Drying time has followed or not (As per the manufacturer instructions)
24.Painting work | 9 Ensure all loose and small particles are removed and smoothen the surface with sand paper.
24.Painting work | Painting application 10 To check the application of coat as per specs
24.Painting work | 11 To check the no of coat applied
24.Painting work | 12 To check for over all coverage and any brush marks
24.Painting work | 13 To check any incomplete and addition and alteration
24.Painting work | 14 To check for cleaning in flooring,doors,windows glasses after painting
25.External drainage | 1 External drainage layout available/Provided
25.External drainage | 2 Type of Drain system Normal/CLEAN OUT
25.External drainage | 3 To check sufficient gap between wall & pipes
25.External drainage | 4 To check the sizes and type of pipes
25.External drainage | 5 To check the Manholes provided as required intervals
25.External drainage | 6 To check the inspection champer/Manholes plastered
25.External drainage | 7 Slope of the entire drainage as specified
25.External drainage | 8 Joining of pipes done properly
25.External drainage | 9 Check the branch lines joining main sewer line as required
26.Completion | 1 Paving & Landscaping
26.Completion | 2 All doors and door hardware installed
26.Completion | 3 Ceiling & Wall finishes completed
26.Completion | 4 All flooring system completed
26.Completion | 5 All windows installed
26.Completion | 6 All Plumbing fixures installed ( W.C,Wash basins,etc.,)
26.Completion | 7 Ventilation system installed
26.Completion | 8 Heating system installed
26.Completion | 9 All Electrical system instaleed (Lights,Fans,etc.,)
26.Completion | 10 All Structual / finishing works completed as per drawing/Specs
26.Completion | 11 All Boudary wall work and Main gate installation done
26.Completion | 12 All the surrounding area cleaning has done aginst wastes,Constuction materials,etc.,
27.Testing & Commisioning | 1 Visual inspection of HVAC equipment
27.Testing & Commisioning | 2 Test an verify functionality of Airconditioning
27.Testing & Commisioning | 3 Check chilled/Hot water working proper
27.Testing & Commisioning | 4 Check the functionality of Exhaust fans systems
27.Testing & Commisioning | 5 Check airflow direction & Exhaust fan locations are corrct
27.Testing & Commisioning | 6 Verify electrical panels are labeled correctly
27.Testing & Commisioning | 7 Check main breaker operation and trip settings
27.Testing & Commisioning | 8 Ensure all circuit breakers are functioning
27.Testing & Commisioning | 9 Confirm proper installation of lighting fixures
27.Testing & Commisioning | 10 Test the operation of lighting controls (Manual/Sensor)
27.Testing & Commisioning | 11 Verify Emergency lightings if any
27.Testing & Commisioning | 12 Verify the Correct installation of pipes,valves and fixtures
27.Testing & Commisioning | 13 Check the water presure
27.Testing & Commisioning | 14 Visual insp of drainage syastems and vents
27.Testing & Commisioning | 15 Verify the installation of BAS components(Sensors,Controllers)
27.Testing & Commisioning | 16 Inspect exterior walls ,Windows roof for leaks and damage
27.Testing & Commisioning | 17 Test the operation of Doors /Windows
3.Footing | 1 The setback of the building as per the drawing
3.Footing | Front side of the building
3.Footing | Left side of the building
3.Footing | Right side of the building
3.Footing | Rear side of the building
3.Footing | 2 Nearest Road level/Plinth level/Interlock level marking at the site
3.Footing | 3 Structural grid line and architectural grid lines are provided as per the drawing
3.Footing | 4 Footing formwork including form oil applied and laid to the correct dimensions including line, level and plumb checked.
3.Footing | 5 Supporting of the formwork
3.Footing | 6 All columns sizes and orientation
3.Footing | 7 Sizes (length and Diameter) of re-bar of the footings
3.Footing | 8 Spacing of re-bar as per the drawing
3.Footing | 9 Direction and Alignment of the re-bar
3.Footing | 10 Right angle of the footing & Column
3.Footing | 11 Cover of concrete around reinforcement steel maintained as per requirement
3.Footing | 12 Separator (Chair Bar) is provided properly between top and bottom re-bar.
3.Footing | 13 Development length of the re-bar of the footing as per requirement
3.Footing | 14 Sizes (length and Diameter) of re-bar of the Columns
3.Footing | 15 Reinforcement bars are free from rust,mill scales, cleaned concrete droppings and any other such impurities
3.Footing | 16 Sizes/Spacings of the stirrups of re-bar of the Columns
4.Retaining wall steel fabrication and Formwork | 1 Formwork including form oil applied and laid to the correct dimensions including line, level and plumb checked.
4.Retaining wall steel fabrication and Formwork | 2 The verticality of the retaining shuttering using a plumb
4.Retaining wall steel fabrication and Formwork | 3 The dimensions of Retaining wall (length, breadth and depth).
4.Retaining wall steel fabrication and Formwork | 4 Right angle at the corners of wall shuttering
4.Retaining wall steel fabrication and Formwork | 5 The proper support is given to the wall or not
4.Retaining wall steel fabrication and Formwork | 6 All the supports are rested over the stable/rigid place?
4.Retaining wall steel fabrication and Formwork | 7 All gaps are properly sealed or not
4.Retaining wall steel fabrication and Formwork | 8 The marking of concrete pouring level.
4.Retaining wall steel fabrication and Formwork | 9 Provisions of cover blocks at the top
4.Retaining wall steel fabrication and Formwork | 10 Provisions of butterflies ,wherever the Blockwork comes in thewall surface
4.Retaining wall steel fabrication and Formwork | 11 Any MEP provisions has provided or not
5.Short column shuttering | 1 Shuttering material is good ?
5.Short column shuttering | 2 The verticality of the column shuttering using a plumb
5.Short column shuttering | 3 The Horizontal Line alignment of th columns
5.Short column shuttering | 4 The dimensions of column (length, breadth and depth).
5.Short column shuttering | 5 Reinforcement of the column as per the drawing
5.Short column shuttering | 6 Reinforcement bars are free from rust,mill scales, cleaned concrete droppings and any other such impurities
5.Short column shuttering | 7 The proper support is given to the column or not
5.Short column shuttering | 8 Coverblocks are provided to main rebar/stirrups
5.Short column shuttering | 9 All gaps are properly sealed or not
5.Short column shuttering | 10 The marking of concrete pouring level.(The bottom of the beam level)
6.Plinth beam | 1 Formwork including form oil applied and laid to the correct dimensions including line, level and plumb checked.
6.Plinth beam | 2 The verticality and Horizontal line alignment of the Plinth Beam
6.Plinth beam | 3 The dimensions of Plinth Beam (length, breadth and depth).
6.Plinth beam | 4 Top level of the Plinth beam
6.Plinth beam | 5 Right angle of the Plinth
6.Plinth beam | 6 The proper support is given to the plinth beam or not
6.Plinth beam | 7 Reinforcement length,diameter and no. of bars laid as per the drawings
6.Plinth beam | 8 Curtailment and Extra end supports and continuous supports are provided as per the drawing requirement
6.Plinth beam | 9 Development lengths are provided as per required
6.Plinth beam | 10 All gaps are properly sealed or not
6.Plinth beam | 11 Reinforcement bars are free from rust,mill scales, cleaned concrete droppings and any other such impurities
6.Plinth beam | 12 Coverblocks are provided to main rebar/stirrups
6.Plinth beam | 13 All gaps are properly sealed or not
6.Plinth beam | 14 Any MEP provisions has provided or not
7.Bitumen application | 1 Coverage of the Bitumenous is sufficient
7.Bitumen application | 2 Wastes ,debris,shutters,steels are removed from the Backfilling area
7.Bitumen application | 3 10cm offset bitumin application done from the footing & wall?
7.Bitumen application | 4 All the block joints bitumen appliation done properly?
8.Water Proofing | 1 Cleaning the surface and removing loose material, if any.
8.Water Proofing | 2 Sealing of joints.and screeding with triangular fillet between the wall and floor joints
8.Water Proofing | 3 Type of water proofing
8.Water Proofing | a.Cementititios
8.Water Proofing | The material approved for the wet area water proofing
8.Water Proofing | The proportion of mixing with proposed material is done as per manufacturers specifications
8.Water Proofing | The duration has followed between the first coat and second coat
8.Water Proofing | b.Membrane
8.Water Proofing | Primer (Solvent based primer) is done and allowed to dry.
8.Water Proofing | All membrane sheet is well sticked with the screed and there is no air gap.
8.Water Proofing | The joint provisions of the water proofing membrane is proper or not.If roof joint has done towards the drain slope
8.Water Proofing | Overlap of the membrane is 10 cm minimum.
8.Water Proofing | 4 Protection sheet provided or not
8.Water Proofing | 5 Waterproofing is done around the water outlets, and made proper water exit.
8.Water Proofing | 5 Water ponding done for 3 days
8.Water Proofing | 6 Is there any marks observed for leakages,Dampness, on the ceiling below
8.Water Proofing | 7 Is there any seepage observed on the wall of floor below
9.Backfilling | 1 Number of layer
9.Backfilling | 1 The approved materials are used
9.Backfilling | 2 The approved materials are used
9.Backfilling | 3 The approved materials are used
9.Backfilling | 4 The process of filling and watering and compaction shall be carried out till the required level
9.Backfilling | 5 Is there any structural members damaged during the Backfilling process?
9.Backfilling | 6 FDT result submitted for review and approval of the next stage?
9.Backfilling